## Objects
Priority | Overall Status |  | Script | Date of data | Snowflake | ETA | Sort | Comments | Azure Container Name | Azure Logic App Name | Azure Logic App PRD Scheduled time, UTC | Expected time in S3 landing PRD, UTC | AWS S3 |  |  | Tags | landing | [5 empty] | conformed |  |  |  |  | DW Dim/Fact (PBIGOV schema)
| Script | SF | Developer | in S3 raw | Developer | SF development | [6 empty] | Bucket | Root folder path | Subfolder Name |  | Snowpipe | table | stream | existing sp | task | task schedule | table | view | sp | task | task trigger/schedule | table | view
High | Completed | Not started | Abhay/Samir | 2025-03-10 | Maddie/Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-apps-full | la-pbigov-dev-apps | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | apps | Dimension table | PIPE_PBIGOV_APPS | PBIGOV_APPS | STM_PBIGOV_APPS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_APPS | USING CRON 0 8 * * * UTC | PBIGOV_APPS | V_PBIGOV_DIMAPPS | PBIGOV_DIMAPPS_ADD | TASK_PBIGOV_DIMAPPS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMAPPS | PBIGOV.V_DIMAPPS |  | Need to discuss
High | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasources_scan | Dimension table, Scanner data | PIPE_PBIGOV_ARTIFACTDATASOURCEDETAILS_SCAN | PBIGOV_ARTIFACTDATASOURCEDETAILS_SCAN | STM_PBIGOV_ARTIFACTDATASOURCEDETAILS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ARTIFACTDATASOURCEDETAILS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_ARTIFACTDATASOURCEDETAILS_SCAN | V_PBIGOV_DIMARTIFACTDATASOURCEDETAILS_SCAN | PBIGOV_DIMARTIFACTDATASOURCEDETAILS_SCAN_ADD | TASK_PBIGOV_DIMARTIFACTDATASOURCEDETAILS_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMARTIFACTDATASOURCEDETAILS | PBIGOV.V_DIMARTIFACTDATASOURCEDETAILS |  | in progress
High | In progress | Not started | Samir | 2025-03-19 | Ashleigh/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetdatasources_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETDATASOURCES_SCAN | PBIGOV_ARTIFACTDATASOURCES_SCAN | STM_PBIGOV_ARTIFACTDATASOURCES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ARTIFACTDATASOURCES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_ARTIFACTDATASOURCES_SCAN | V_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | PBIGOV_DIMARTIFACTDATASOURCES_SCAN_ADD | TASK_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMARTIFACTDATASOURCES | PBIGOV.V_DIMARTIFACTDATASOURCES |  | completed
High | In progress | Not started | Samir | 2025-03-19 | Ashleigh/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowdatasources_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWDATASOURCES_SCAN | PBIGOV_ARTIFACTDATASOURCES_SCAN | STM_PBIGOV_ARTIFACTDATASOURCES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ARTIFACTDATASOURCES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_ARTIFACTDATASOURCES_SCAN | V_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | PBIGOV_DIMARTIFACTDATASOURCES_SCAN_ADD | TASK_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMARTIFACTDATASOURCES | PBIGOV.V_DIMARTIFACTDATASOURCES |  | completed
High | In progress | Not started | Samir | 2025-03-19 | Ashleigh/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datamartdatasources_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAMARTDATASOURCES_SCAN | PBIGOV_ARTIFACTDATASOURCES_SCAN | STM_PBIGOV_ARTIFACTDATASOURCES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ARTIFACTDATASOURCES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_ARTIFACTDATASOURCES_SCAN | V_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | PBIGOV_DIMARTIFACTDATASOURCES_SCAN_ADD | TASK_PBIGOV_DIMARTIFACTDATASOURCES_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMARTIFACTDATASOURCES | PBIGOV.V_DIMARTIFACTDATASOURCES |  | completed
High | Completed | Not started | Ashleigh/Samir | 2025-03-10 | Ashleigh/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-capacities-full | la-pbigov-dev-capacities | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | capacities | Dimension table | PIPE_PBIGOV_CAPACITIES | PBIGOV_CAPACITIES | STM_PBIGOV_CAPACITIES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_CAPACITIES | USING CRON 0 8 * * * UTC | PBIGOV_CAPACITIES | V_PBIGOV_DIMCAPACITIES | PBIGOV_DIMCAPACITIES_ADD | TASK_PBIGOV_DIMCAPACITIES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMCAPACITIES | PBIGOV.V_DIMCAPACITIES |  | skipped
High | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dashboards | Dimension table | PIPE_PBIGOV_DASHBOARDS | PBIGOV_DASHBOARDS | STM_PBIGOV_DASHBOARDS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DASHBOARDS | USING CRON 0 4 * * * UTC | PBIGOV_DASHBOARDS | V_PBIGOV_DIMDASHBOARDS | PBIGOV_DIMDASHBOARDS_ADD | TASK_PBIGOV_DIMDASHBOARDS | USING CRON 0 5 * * * UTC | PBIGOV.DIMDASHBOARDS | PBIGOV.V_DIMDASHBOARDS |  | need research
High | In progress | Not started | Samir | 2025-03-19 | Khim/Ruslan |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dashboards_scan | Dimension table, Scanner data | PIPE_PBIGOV_DASHBOARDS_SCAN | PBIGOV_DASHBOARDS_SCAN | STM_PBIGOV_DASHBOARDS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DASHBOARDS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DASHBOARDS_SCAN | V_PBIGOV_DIMDASHBOARDS_SCAN | PBIGOV_DIMDASHBOARDS_SCAN_ADD | TASK_PBIGOV_DIMDASHBOARDS_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDASHBOARDS | PBIGOV.V_DIMDASHBOARDS | <Name> | assigned to <Name>
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dashboardtiles_scan | Dimension table, Scanner data | PIPE_PBIGOV_DASHBOARDTILES_SCAN | PBIGOV_DASHBOARDTILES_SCAN | STM_PBIGOV_DASHBOARDTILES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DASHBOARDTILES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DASHBOARDTILES_SCAN | V_PBIGOV_DIMDASHBOARDTILES_SCAN | PBIGOV_DIMDASHBOARDTILES_SCAN_ADD | TASK_PBIGOV_DIMDASHBOARDTILES_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDASHBOARDTILES | PBIGOV.V_DIMDASHBOARDTILES | empty | free
Medium | In progress | Not started | Samir | TBD |  |  | 1 | Data is not extracted yet | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowpartitions_json | Dimension table, Dataflow Json parsing | PIPE_PBIGOV_DATAFLOWPARTITIONS_JSON_JSON | PBIGOV_DATAFLOWPARTITIONS_JSON | STM_PBIGOV_DATAFLOWPARTITIONS_JSON | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWPARTITIONS_JSON | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWPARTITIONS_JSON | V_PBIGOV_DIMDATAFLOWPARTITIONS_JSON | PBIGOV_DIMDATAFLOWPARTITIONS_JSON_ADD | TASK_PBIGOV_DIMDATAFLOWPARTITIONS_JSON | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATAFLOWPARTITIONS | PBIGOV.V_DIMDATAFLOWPARTITIONS |  | data is available
Medium | In progress | Not started | Samir | TBD |  |  | 1 | Data is not extracted yet | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowqueries_json | Dimension table, Dataflow Json parsing | PIPE_PBIGOV_DATAFLOWQUERIES_JSON | PBIGOV_DATAFLOWQUERIES_JSON | STM_PBIGOV_DATAFLOWQUERIES_JSON | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWQUERIES_JSON | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWQUERIES_JSON | V_PBIGOV_DIMDATAFLOWQUERIES_JSON | PBIGOV_DIMDATAFLOWQUERIES_JSON_ADD | TASK_PBIGOV_DIMDATAFLOWQUERIES_JSON | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATAFLOWQUERIES | PBIGOV.V_DIMDATAFLOWQUERIES
High | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflows | Dimension table | PIPE_PBIGOV_DATAFLOWS | PBIGOV_DATAFLOWS | STM_PBIGOV_DATAFLOWS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWS | USING CRON 0 8 * * * UTC | PBIGOV_DATAFLOWS | V_PBIGOV_DIMDATAFLOWS | PBIGOV_DIMDATAFLOWS_ADD | TASK_PBIGOV_DIMDATAFLOWS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATAFLOWS | PBIGOV.V_DIMDATAFLOWS
Medium | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflows_json | Dimension table, Dataflow Json parsing | PIPE_PBIGOV_DATAFLOWS_JSON | PBIGOV_DATAFLOWS_JSON | STM_PBIGOV_DATAFLOWS_JSON | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWS_JSON | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWS_JSON | V_PBIGOV_DIMDATAFLOWS_JSON | PBIGOV_DIMDATAFLOWS_JSON_ADD | TASK_PBIGOV_DIMDATAFLOWS_JSON | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATAFLOWS | PBIGOV.V_DIMDATAFLOWS
High | In progress | Not started | Samir | 2025-03-19 | Khim/Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflows_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWS_SCAN | PBIGOV_DATAFLOWS_SCAN | STM_PBIGOV_DATAFLOWS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATAFLOWS_SCAN | V_PBIGOV_DIMDATAFLOWS | PBIGOV_DIMDATAFLOWS_ADD | TASK_PBIGOV_DIMDATAFLOWS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATAFLOWS | PBIGOV.V_DIMDATAFLOWS
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datamarts_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAMARTS_SCAN | PBIGOV_DATAMARTS_SCAN | STM_PBIGOV_DATAMARTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAMARTS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATAMARTS_SCAN | V_PBIGOV_DIMDATAMARTS_SCAN | PBIGOV_DIMDATAMARTS_SCAN_ADD | TASK_PBIGOV_DIMDATAMARTS_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATAMARTS | PBIGOV.V_DIMDATAMARTS
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetcolumns_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETCOLUMNS_SCAN | PBIGOV_DATASETCOLUMNS_SCAN | STM_PBIGOV_DATASETCOLUMNS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETCOLUMNS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETCOLUMNS_SCAN | V_PBIGOV_DIMDATASETCOLUMNS_SCAN | PBIGOV_DIMDATASETCOLUMNS_SCAN_ADD | TASK_PBIGOV_DIMDATASETCOLUMNS_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATASETCOLUMNS | PBIGOV.V_DIMDATASETCOLUMNS
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetmeasures_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETMEASURES_SCAN | PBIGOV_DATASETMEASURES_SCAN | STM_PBIGOV_DATASETMEASURES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETMEASURES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETMEASURES_SCAN | V_PBIGOV_DIMDATASETMEASURES_SCAN | PBIGOV_DIMDATASETMEASURES_SCAN_ADD | TASK_PBIGOV_DIMDATASETMEASURES_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATASETMEASURES | PBIGOV.V_DIMDATASETMEASURES
High | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasets | Dimension table | PIPE_PBIGOV_DATASETS | PBIGOV_DATASETS | STM_PBIGOV_DATASETS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETS | USING CRON 0 8 * * * UTC | PBIGOV_DATASETS | V_PBIGOV_DIMDATASETS | PBIGOV_DIMDATASETS_ADD | TASK_PBIGOV_DIMDATASETS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATASETS | PBIGOV.V_DIMDATASETS
High | In progress | Not started | Samir | 2025-03-19 | Khim/Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasets_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETS_SCAN | PBIGOV_DATASETS_SCAN | STM_PBIGOV_DATASETS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATASETS_SCAN | V_PBIGOV_DIMDATASETS | PBIGOV_DIMDATASETS_ADD | TASK_PBIGOV_DIMDATASETS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATASETS | PBIGOV.V_DIMDATASETS
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasettables_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETTABLES_SCAN | PBIGOV_DATASETTABLES_SCAN | STM_PBIGOV_DATASETTABLES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETTABLES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETTABLES_SCAN | V_PBIGOV_DIMDATASETTABLES_SCAN | PBIGOV_DIMDATASETTABLES_SCAN_ADD | TASK_PBIGOV_DIMDATASETTABLES_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATASETTABLES | PBIGOV.V_DIMDATASETTABLES
Medium | Completed | Not started | SiaChing/Samir | 2025-03-10 | Maddie/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-pipelines-full | la-pbigov-dev-pipelines | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | deploymentpipelines | Dimension table | PIPE_PBIGOV_DEPLOYMENTPIPELINES | PBIGOV_DEPLOYMENTPIPELINES | STM_PBIGOV_DEPLOYMENTPIPELINES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DEPLOYMENTPIPELINES | USING CRON 0 8 * * * UTC | PBIGOV_DEPLOYMENTPIPELINES | V_PBIGOV_DIMDEPLOYMENTPIPELINES | PBIGOV_DIMDEPLOYMENTPIPELINES_ADD | TASK_PBIGOV_DIMDEPLOYMENTPIPELINES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDEPLOYMENTPIPELINES | PBIGOV.V_DIMDEPLOYMENTPIPELINES
Medium | Completed | Not started | SiaChing/Samir | 2025-03-10 | Maddie/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-pipelines-full | la-pbigov-dev-pipelines | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | deploymentpipelinestages | Dimension table | PIPE_PBIGOV_DEPLOYMENTPIPELINESTAGES | PBIGOV_DEPLOYMENTPIPELINESTAGES | STM_PBIGOV_DEPLOYMENTPIPELINESTAGES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DEPLOYMENTPIPELINESTAGES | USING CRON 0 8 * * * UTC | PBIGOV_DEPLOYMENTPIPELINESTAGES | V_PBIGOV_DIMDEPLOYMENTPIPELINESTAGES | PBIGOV_DIMDEPLOYMENTPIPELINESTAGES_ADD | TASK_PBIGOV_DIMDEPLOYMENTPIPELINESTAGES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDEPLOYMENTPIPELINESTAGES | PBIGOV.V_DIMDEPLOYMENTPIPELINESTAGES
Low | Not started | Not started | TBD | TBD |  |  | 1 | Data is not extracted yet | ci-dev-df-pbiapi-awss3-domains-full | la-pbigov-dev-domains | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | domains | Dimension table | PIPE_PBIGOV_DOMAINS | PBIGOV_DOMAINS | STM_PBIGOV_DOMAINS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DOMAINS | USING CRON 0 4 * * * UTC | PBIGOV_DOMAINS | V_PBIGOV_DIMDOMAINS | PBIGOV_DIMDOMAINS_ADD | TASK_PBIGOV_DIMDOMAINS | USING CRON 0 5 * * * UTC | PBIGOV.DIMDOMAINS | PBIGOV.V_DIMDOMAINS
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | explorations_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_EXPLORATIONS_SCAN | PBIGOV_EXPLORATIONS_SCAN | STM_PBIGOV_EXPLORATIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EXPLORATIONS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EXPLORATIONS_SCAN | V_PBIGOV_DIMEXPLORATIONS_SCAN | PBIGOV_DIMEXPLORATIONS_SCAN_ADD | TASK_PBIGOV_DIMEXPLORATIONS_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMEXPLORATIONS | PBIGOV.V_DIMEXPLORATIONS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datapipelines_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_DATAPIPELINES_SCAN | PBIGOV_DATAPIPELINES_SCAN | STM_PBIGOV_DATAPIPELINES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAPIPELINES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAPIPELINES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | environments_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_ENVIRONMENTS_SCAN | PBIGOV_ENVIRONMENTS_SCAN | STM_PBIGOV_ENVIRONMENTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ENVIRONMENTS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_ENVIRONMENTS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | Completed | Not started | Samir | 2025-04-17 |  |  | 1 |  | ci-dev-df-pbiapi-awss3-gateways-full | la-pbigov-dev-gateways | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | gatewayclusterpermissions | Dimension table | PIPE_PBIGOV_GATEWAYCLUSTERPERMISSIONS | PBIGOV_GATEWAYCLUSTERPERMISSIONS | STM_PBIGOV_GATEWAYCLUSTERPERMISSIONS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_GATEWAYCLUSTERPERMISSIONS | USING CRON 0 4 * * * UTC | PBIGOV_GATEWAYCLUSTERPERMISSIONS | V_PBIGOV_DIMGATEWAYCLUSTERPERMISSIONS | PBIGOV_DIMGATEWAYCLUSTERPERMISSIONS_ADD | TASK_PBIGOV_DIMGATEWAYCLUSTERPERMISSIONS | USING CRON 0 5 * * * UTC | PBIGOV.DIMGATEWAYCLUSTERPERMISSIONS | PBIGOV.V_DIMGATEWAYCLUSTERPERMISSIONS
High | Completed | Not started | Samir | 2025-04-17 | Ashleigh/Ruslan |  | 1 |  | ci-dev-df-pbiapi-awss3-gateways-full | la-pbigov-dev-gateways | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | gatewayclusters | Dimension table | PIPE_PBIGOV_GATEWAYCLUSTERS | PBIGOV_GATEWAYCLUSTERS | STM_PBIGOV_GATEWAYCLUSTERS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_GATEWAYCLUSTERS | USING CRON 0 8 * * * UTC | PBIGOV_GATEWAYCLUSTERS | V_PBIGOV_DIMGATEWAYCLUSTERS | PBIGOV_DIMGATEWAYCLUSTERS_ADD | TASK_PBIGOV_DIMGATEWAYCLUSTERS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMGATEWAYCLUSTERS | PBIGOV.V_DIMGATEWAYCLUSTERS
High | Completed | Not started | Samir | 2025-04-17 | Ashleigh/Ruslan |  | 1 |  | ci-dev-df-pbiapi-awss3-gateways-full | la-pbigov-dev-gateways | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | gatewayinstances | Dimension table | PIPE_PBIGOV_GATEWAYINSTANCES | PBIGOV_GATEWAYINSTANCES | STM_PBIGOV_GATEWAYINSTANCES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_GATEWAYINSTANCES | USING CRON 0 8 * * * UTC | PBIGOV_GATEWAYINSTANCES | V_PBIGOV_DIMGATEWAYINSTANCES | PBIGOV_DIMGATEWAYINSTANCES_ADD | TASK_PBIGOV_DIMGATEWAYINSTANCES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMGATEWAYINSTANCES | PBIGOV.V_DIMGATEWAYINSTANCES
High | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reports | Dimension table | PIPE_PBIGOV_REPORTS | PBIGOV_REPORTS | STM_PBIGOV_REPORTS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REPORTS | USING CRON 0 8 * * * UTC | PBIGOV_REPORTS | V_PBIGOV_DIMREPORTS | PBIGOV_DIMREPORTS_ADD | TASK_PBIGOV_DIMREPORTS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREPORTS | PBIGOV.V_DIMREPORTS
High | In progress | Not started | Samir | 2025-03-19 | Khim/Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reports_scan | Dimension table, Scanner data | PIPE_PBIGOV_REPORTS_SCAN | PBIGOV_REPORTS_SCAN | STM_PBIGOV_REPORTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REPORTS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_REPORTS_SCAN | V_PBIGOV_DIMREPORTS | PBIGOV_DIMREPORTS_ADD | TASK_PBIGOV_DIMREPORTS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREPORTS | PBIGOV.V_DIMREPORTS
Low | In progress | Not started | Samir | TBD |  |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | workbooks | Dimension table | PIPE_PBIGOV_WORKBOOKS | PBIGOV_WORKBOOKS | STM_PBIGOV_WORKBOOKS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WORKBOOKS | USING CRON 0 4 * * * UTC | PBIGOV_WORKBOOKS | V_PBIGOV_DIMWORKBOOKS | PBIGOV_DIMWORKBOOKS_ADD | TASK_PBIGOV_DIMWORKBOOKS | USING CRON 0 5 * * * UTC | PBIGOV.DIMWORKBOOKS | PBIGOV.V_DIMWORKBOOKS
High | In progress | In progress | Samir | TBD | Ruslan |  | 1 |  | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | workspaces | Dimension table | PIPE_PBIGOV_WORKSPACES | PBIGOV_WORKSPACES | STM_PBIGOV_WORKSPACES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WORKSPACES | USING CRON 0 8 * * * UTC | PBIGOV_WORKSPACES | V_PBIGOV_DIMWORKSPACES | PBIGOV_DIMWORKSPACES_ADD | TASK_PBIGOV_DIMWORKSPACES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMWORKSPACES | PBIGOV.V_DIMWORKSPACES
High | In progress | In progress | Samir | 2025-03-19 | Ruslan | 2025-05-12 | 1 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | workspaces_scan | Dimension table, Scanner data | PIPE_PBIGOV_WORKSPACES_SCAN | PBIGOV_WORKSPACES_SCAN | STM_PBIGOV_WORKSPACES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WORKSPACES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_WORKSPACES_SCAN | V_PBIGOV_DIMWORKSPACES | PBIGOV_DIMWORKSPACES_ADD | TASK_PBIGOV_DIMWORKSPACES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMWORKSPACES | PBIGOV.V_DIMWORKSPACES
High | Completed | Not started | Toghrul/Samir | 2025-03-10 | Ashleigh/Ruslan | 2025-05-09 | 1 |  | ci-dev-df-pbiapi-awss3-activitylogs-incr | la-pbigov-dev-activitylogs | Daily, 01:00 AM | Daily, 03:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | activitylogs | Fact table | PIPE_PBIGOV_ACTIVITYLOGS | PBIGOV_ACTIVITYLOGS | STM_PBIGOV_ACTIVITYLOGS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ACTIVITYLOGS | USING CRON 0 8 * * * UTC | PBIGOV_ACTIVITYLOGS | V_PBIGOV_FACTACTIVITYLOGS | PBIGOV_FACTACTIVITYLOGS_ADD | TASK_PBIGOV_FACTACTIVITYLOGS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.FACTACTIVITYLOGS | PBIGOV.V_FACTACTIVITYLOGS
Medium | Not started | Not started | TBD | TBD |  |  | 1 | Data is not extracted yet | ci-dev-df-pbimodel-awss3-capmetrics-incr | la-pbigov-dev-capmetrics | 1) Daily, 01:00 AM 2) Hourly | 1) Daily, 03:00 AM 2) Hourly | s3-eip-dev-uea1-landing-001 | landing/data/pbi | artifactmetrics | Fact table, Capacity Metrics data | PIPE_PBIGOV_ARTIFACTMETRICS | PBIGOV_ARTIFACTMETRICS | STM_PBIGOV_ARTIFACTMETRICS | TABLE_LOAD_DELTA_ADD | TASK_PBIGOV_ARTIFACTMETRICS | USING CRON 0 8 * * * UTC | PBIGOV_ARTIFACTMETRICS | V_PBIGOV_FACT_ARTIFACTMETRICS | PBIGOV_FACTARTIFACTMETRICS_ADD | TASK_PBIGOV_FACTARTIFACTMETRICS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.FACTARTIFACTMETRICS | PBIGOV.V_FACTARTIFACTMETRICS
High | Completed | Not started | Abhay/Samir | 2025-03-10 | Maddie/Ruslan | 2025-05-20 | 1 |  | ci-dev-df-pbiapi-awss3-lastrefreshes-incr | la-pbigov-dev-lastrefreshes | 1) Daily, 01:00 AM 2) Hourly | 1) Daily, 02:00 AM 2) Hourly | s3-eip-dev-uea1-landing-001 | landing/data/pbi | lastrefreshes | Fact table | PIPE_PBIGOV_LASTREFRESHES | PBIGOV_LASTREFRESHES | STM_PBIGOV_LASTREFRESHES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_LASTREFRESHES | USING CRON 0 8 * * * UTC | PBIGOV_LASTREFRESHES | V_PBIGOV_FACTLASTREFRESHES | PBIGOV_FACTLASTREFRESHES_ADD | TASK_PBIGOV_FACTLASTREFRESHES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.FACTLASTREFRESHES | PBIGOV.V_FACTLASTREFRESHES
Medium | Completed | Not started | Abhay/Samir | 2025-03-10 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-apps-full | la-pbigov-dev-apps | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | appusers | Dimension table | PIPE_PBIGOV_APPUSERS | PBIGOV_APPUSERS | STM_PBIGOV_APPUSERS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_APPUSERS | USING CRON 0 4 * * * UTC | PBIGOV_APPUSERS | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | capacityusers | Dimension table, Scanner data | PIPE_PBIGOV_CAPACITYUSERS_SCAN | PBIGOV_CAPACITYUSERS_SCAN | STM_PBIGOV_CAPACITYUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_CAPACITYUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_CAPACITYUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dashboardusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DASHBOARDUSERS_SCAN | PBIGOV_DASHBOARDUSERS_SCAN | STM_PBIGOV_DASHBOARDUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DASHBOARDUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DASHBOARDUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWUSERS_SCAN | PBIGOV_DATAFLOWUSERS_SCAN | STM_PBIGOV_DATAFLOWUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datamartusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAMARTUSERS_SCAN | PBIGOV_DATAMARTUSERS_SCAN | STM_PBIGOV_DATAMARTUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAMARTUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAMARTUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datapipelineusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAPIPELINEUSERS_SCAN | PBIGOV_DATAPIPELINEUSERS_SCAN | STM_PBIGOV_DATAPIPELINEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAPIPELINEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAPIPELINEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETUSERS_SCAN | PBIGOV_DATASETUSERS_SCAN | STM_PBIGOV_DATASETUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | deploymentpipelineusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_DEPLOYMENTPIPELINEUSERS_SCAN | PBIGOV_DEPLOYMENTPIPELINEUSERS_SCAN | STM_PBIGOV_DEPLOYMENTPIPELINEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DEPLOYMENTPIPELINEUSERS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DEPLOYMENTPIPELINEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | environmentusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_ENVIRONMENTUSERS_SCAN | PBIGOV_ENVIRONMENTUSERS_SCAN | STM_PBIGOV_ENVIRONMENTUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ENVIRONMENTUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_ENVIRONMENTUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | eventhouseusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_EVENTHOUSEUSERS_SCAN | PBIGOV_EVENTHOUSEUSERS_SCAN | STM_PBIGOV_EVENTHOUSEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EVENTHOUSEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EVENTHOUSEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | eventstreamusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_EVENTSTREAMUSERS_SCAN | PBIGOV_EVENTSTREAMUSERS_SCAN | STM_PBIGOV_EVENTSTREAMUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EVENTSTREAMUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EVENTSTREAMUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | explorationusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_EXPLORATIONUSERS_SCAN | PBIGOV_EXPLORATIONUSERS_SCAN | STM_PBIGOV_EXPLORATIONUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EXPLORATIONUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EXPLORATIONUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | kqldatabaseusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_KQLDATABASEUSERS_SCAN | PBIGOV_KQLDATABASEUSERS_SCAN | STM_PBIGOV_KQLDATABASEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_KQLDATABASEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_KQLDATABASEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | lakehouseusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_LAKEHOUSEUSERS_SCAN | PBIGOV_LAKEHOUSEUSERS_SCAN | STM_PBIGOV_LAKEHOUSEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_LAKEHOUSEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_LAKEHOUSEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | notebookusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_NOTEBOOKUSERS_SCAN | PBIGOV_NOTEBOOKUSERS_SCAN | STM_PBIGOV_NOTEBOOKUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_NOTEBOOKUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_NOTEBOOKUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | orgappusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_ORGAPPUSERS_SCAN | PBIGOV_ORGAPPUSERS_SCAN | STM_PBIGOV_ORGAPPUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ORGAPPUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_ORGAPPUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reflexusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_REFLEXUSERS_SCAN | PBIGOV_REFLEXUSERS_SCAN | STM_PBIGOV_REFLEXUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REFLEXUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_REFLEXUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reportsusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_REPORTUSERS_SCAN | PBIGOV_REPORTUSERS_SCAN | STM_PBIGOV_REPORTUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REPORTUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_REPORTUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | sqlanalyticsendpointusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_SQLANALYTICSENDPOINTUSERS_SCAN | PBIGOV_SQLANALYTICSENDPOINTUSERS_SCAN | STM_PBIGOV_SQLANALYTICSENDPOINTUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_SQLANALYTICSENDPOINTUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_SQLANALYTICSENDPOINTUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | sqldatabaseusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_SQLDATABASEUSERS_SCAN | PBIGOV_SQLDATABASEUSERS_SCAN | STM_PBIGOV_SQLDATABASEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_SQLDATABASEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_SQLDATABASEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | warehouseusers_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_WAREHOUSEUSERS_SCAN | PBIGOV_WAREHOUSEUSERS_SCAN | STM_PBIGOV_WAREHOUSEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WAREHOUSEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_WAREHOUSEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | TBD | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | workspaceusers | Dimension table | PIPE_PBIGOV_WORKSPACEUSERS | PBIGOV_WORKSPACEUSERS | STM_PBIGOV_WORKSPACEUSERS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WORKSPACEUSERS | USING CRON 0 4 * * * UTC | PBIGOV_WORKSPACEUSERS | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Medium | In progress | Not started | Samir | 2025-03-19 | Ashleigh |  | 2 | ARTIFACTUSERS | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | workspaceusers_scan | Dimension table, Scanner data | PIPE_PBIGOV_WORKSPACEUSERS_SCAN | PBIGOV_WORKSPACEUSERS_SCAN | STM_PBIGOV_WORKSPACEUSERS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WORKSPACEUSERS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_WORKSPACEUSERS_SCAN | V_PBIGOV_DIMARTIFACTUSERS | PBIGOV_DIMARTIFACTUSERS_ADD | TASK_PBIGOV_DIMARTIFACTUSERS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTUSERS | PBIGOV.V_DIMARTIFACTUSERS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | eventhouses_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_EVENTHOUSES_SCAN | PBIGOV_EVENTHOUSES_SCAN | STM_PBIGOV_EVENTHOUSES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EVENTHOUSES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EVENTHOUSES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | eventstreams_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_EVENTSTREAMS_SCAN | PBIGOV_EVENTSTREAMS_SCAN | STM_PBIGOV_EVENTSTREAMS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_EVENTSTREAMS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_EVENTSTREAMS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | kqldatabases_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_KQLDATABASES_SCAN | PBIGOV_KQLDATABASES_SCAN | STM_PBIGOV_KQLDATABASES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_KQLDATABASES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_KQLDATABASES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | lakehouses_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_LAKEHOUSES_SCAN | PBIGOV_LAKEHOUSES_SCAN | STM_PBIGOV_LAKEHOUSES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_LAKEHOUSES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_LAKEHOUSES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | mlexperiments_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_MLEXPERIMENTS_SCAN | PBIGOV_MLEXPERIMENTS_SCAN | STM_PBIGOV_MLEXPERIMENTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_MLEXPERIMENTS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_MLEXPERIMENTS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | mlmodels_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_MLMODELS_SCAN | PBIGOV_MLMODELS_SCAN | STM_PBIGOV_MLMODELS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_MLMODELS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_MLMODELS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | notebooks_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_NOTEBOOKS_SCAN | PBIGOV_NOTEBOOKS_SCAN | STM_PBIGOV_NOTEBOOKS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_NOTEBOOKS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_NOTEBOOKS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | orgapps_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_ORGAPPS_SCAN | PBIGOV_ORGAPPS_SCAN | STM_PBIGOV_ORGAPPS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_ORGAPPS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_ORGAPPS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reflexes_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_REFLEXES_SCAN | PBIGOV_REFLEXES_SCAN | STM_PBIGOV_REFLEXES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REFLEXES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_REFLEXES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | sqlanalyticsendpoints_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_SQLANALYTICSENDPOINTS_SCAN | PBIGOV_SQLANALYTICSENDPOINTS_SCAN | STM_PBIGOV_SQLANALYTICSENDPOINTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_SQLANALYTICSENDPOINTS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_SQLANALYTICSENDPOINTS_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | sqldatabases_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_SQLDATABASES_SCAN | PBIGOV_SQLDATABASES_SCAN | STM_PBIGOV_SQLDATABASES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_SQLDATABASES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_SQLDATABASES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 | Ruslan | 2025-06-04 | 3 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | warehouses_scan | Dimension table, Fabric artifact, Scanner data | PIPE_PBIGOV_WAREHOUSES_SCAN | PBIGOV_WAREHOUSES_SCAN | STM_PBIGOV_WAREHOUSES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_WAREHOUSES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_WAREHOUSES_SCAN | V_PBIGOV_DIMFABRICARTIFACTS | PBIGOV_DIMFABRICARTIFACTS_ADD | TASK_PBIGOV_DIMFABRICARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMFABRICARTIFACTS | PBIGOV.V_DIMFABRICARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 | Toghrul | 2025-05-16 | 4 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowrefreshschedules_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWREFRESHSCHEDULES_SCAN | PBIGOV_DATAFLOWREFRESHSCHEDULES_SCAN | STM_PBIGOV_DATAFLOWREFRESHSCHEDULES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWREFRESHSCHEDULES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATAFLOWREFRESHSCHEDULES_SCAN | V_PBIGOV_DIMREFRESHSCHEDULES | PBIGOV_DIMREFRESHSCHEDULES_ADD | TASK_PBIGOV_DIMREFRESHSCHEDULES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREFRESHSCHEDULES | PBIGOV.V_DIMREFRESHSCHEDULES
High | In progress | Not started | Samir | 2025-03-19 | Toghrul | 2025-05-16 | 4 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetdqrefreshschedules_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETDQREFRESHSCHEDULES_SCAN | PBIGOV_DATASETDQREFRESHSCHEDULES_SCAN | STM_PBIGOV_DATASETDQREFRESHSCHEDULES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETDQREFRESHSCHEDULES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATASETDQREFRESHSCHEDULES_SCAN | V_PBIGOV_DIMREFRESHSCHEDULES | PBIGOV_DIMREFRESHSCHEDULES_ADD | TASK_PBIGOV_DIMREFRESHSCHEDULES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREFRESHSCHEDULES | PBIGOV.V_DIMREFRESHSCHEDULES
High | In progress | Not started | Samir | 2025-03-19 | Toghrul | 2025-05-16 | 4 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetrefreshschedules_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETREFRESHSCHEDULES_SCAN | PBIGOV_DATASETREFRESHSCHEDULES_SCAN | STM_PBIGOV_DATASETREFRESHSCHEDULES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETREFRESHSCHEDULES_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATASETREFRESHSCHEDULES_SCAN | V_PBIGOV_DIMREFRESHSCHEDULES | PBIGOV_DIMREFRESHSCHEDULES_ADD | TASK_PBIGOV_DIMREFRESHSCHEDULES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREFRESHSCHEDULES | PBIGOV.V_DIMREFRESHSCHEDULES
High | Completed | Not started | Toghrul/Samir | 2025-03-10 | Toghrul | 2025-05-16 | 4 |  | ci-dev-df-pbiapi-awss3-refreshschedules-full | la-pbigov-dev-refreshschedules | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | refreshschedules | Dimension table | PIPE_PBIGOV_REFRESHSCHEDULES | PBIGOV_REFRESHSCHEDULES | STM_PBIGOV_REFRESHSCHEDULES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REFRESHSCHEDULES | USING CRON 0 8 * * * UTC | PBIGOV_REFRESHSCHEDULES | V_PBIGOV_DIMREFRESHSCHEDULES | PBIGOV_DIMREFRESHSCHEDULES_ADD | TASK_PBIGOV_DIMREFRESHSCHEDULES | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMREFRESHSCHEDULES | PBIGOV.V_DIMREFRESHSCHEDULES
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowupstreamdataflows_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWUPSTREAMDATAFLOWS_SCAN | PBIGOV_DATAFLOWUPSTREAMDATAFLOWS_SCAN | STM_PBIGOV_DATAFLOWUPSTREAMDATAFLOWS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWUPSTREAMDATAFLOWS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWUPSTREAMDATAFLOWS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowupstreamdatamarts_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWUPSTREAMDATAMARTS_SCAN | PBIGOV_DATAFLOWUPSTREAMDATAMARTS_SCAN | STM_PBIGOV_DATAFLOWUPSTREAMDATAMARTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWUPSTREAMDATAMARTS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWUPSTREAMDATAMARTS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datamartupstreamdataflows_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAMARTUPSTREAMDATAFLOWS_SCAN | PBIGOV_DATAMARTUPSTREAMDATAFLOWS_SCAN | STM_PBIGOV_DATAMARTUPSTREAMDATAFLOWS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAMARTUPSTREAMDATAFLOWS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAMARTUPSTREAMDATAFLOWS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetupstreamdataflows_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETUPSTREAMDATAFLOWS_SCAN | PBIGOV_DATASETUPSTREAMDATAFLOWS_SCAN | STM_PBIGOV_DATASETUPSTREAMDATAFLOWS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETUPSTREAMDATAFLOWS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETUPSTREAMDATAFLOWS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetupstreamdatamarts_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETUPSTREAMDATAMARTS_SCAN | PBIGOV_DATASETUPSTREAMDATAMARTS_SCAN | STM_PBIGOV_DATASETUPSTREAMDATAMARTS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETUPSTREAMDATAMARTS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETUPSTREAMDATAMARTS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
High | In progress | Not started | Samir | 2025-03-19 |  |  | 5 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetupstreamdatasets_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETUPSTREAMDATASETS_SCAN | PBIGOV_DATASETUPSTREAMDATASETS_SCAN | STM_PBIGOV_DATASETUPSTREAMDATASETS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETUPSTREAMDATASETS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETUPSTREAMDATASETS_SCAN | V_PBIGOV_DIMUPSTREAMARTIFACTS | PBIGOV_DIMUPSTREAMARTIFACTS_ADD | TASK_PBIGOV_DIMUPSTREAMARTIFACTS | USING CRON 0 5 * * * UTC | PBIGOV.DIMUPSTREAMARTIFACTS | PBIGOV.V_DIMUPSTREAMARTIFACTS
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 6 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowrelations_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATAFLOWRELATIONS_SCAN | PBIGOV_DATAFLOWRELATIONS_SCAN | STM_PBIGOV_DATAFLOWRELATIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWRELATIONS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWRELATIONS_SCAN | V_PBIGOV_DIMARTIFACTRELATIONS | PBIGOV_DIMARTIFACTRELATIONS_ADD | TASK_PBIGOV_DIMARTIFACTRELATIONS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTRELATIONS | PBIGOV.V_DIMARTIFACTRELATIONS
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 6 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetrelations_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETRELATIONS_SCAN | PBIGOV_DATASETRELATIONS_SCAN | STM_PBIGOV_DATASETRELATIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETRELATIONS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETRELATIONS_SCAN | V_PBIGOV_DIMARTIFACTRELATIONS | PBIGOV_DIMARTIFACTRELATIONS_ADD | TASK_PBIGOV_DIMARTIFACTRELATIONS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTRELATIONS | PBIGOV.V_DIMARTIFACTRELATIONS
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 6 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reportrelations_scan | Dimension table, Scanner data | PIPE_PBIGOV_REPORTRELATIONS_SCAN | PBIGOV_REPORTRELATIONS_SCAN | STM_PBIGOV_REPORTRELATIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REPORTRELATIONS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_REPORTRELATIONS_SCAN | V_PBIGOV_DIMARTIFACTRELATIONS | PBIGOV_DIMARTIFACTRELATIONS_ADD | TASK_PBIGOV_DIMARTIFACTRELATIONS | USING CRON 0 5 * * * UTC | PBIGOV.DIMARTIFACTRELATIONS | PBIGOV.V_DIMARTIFACTRELATIONS
Medium | In progress | Not started | Samir | TBD |  |  | 100 | Data is not extracted yet | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowdatasources_json | Dimension table | PIPE_PBIGOV_DATAFLOWDATASOURCES_JSON | PBIGOV_DATAFLOWDATASOURCES_JSON | STM_PBIGOV_DATAFLOWDATASOURCES_JSON | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATAFLOWDATASOURCES_JSON | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWDATASOURCES_JSON | V_PBIGOV_DIMDATAFLOWDATASOURCES_JSON | PBIGOV_DIMDATAFLOWDATASOURCES_JSON_ADD | TASK_PBIGOV_DIMDATAFLOWDATASOURCES_JSON | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATAFLOWDATASOURCES | PBIGOV.V_DIMDATAFLOWDATASOURCES
Low | In progress | Not started | Samir | 2025-03-19 |  |  | 100 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetexpressions_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETEXPRESSIONS_SCAN | PBIGOV_DATASETEXPRESSIONS_SCAN | STM_PBIGOV_DATASETEXPRESSIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETEXPRESSIONS_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETEXPRESSIONS_SCAN | V_PBIGOV_DIMDATASETEXPRESSIONS_SCAN | PBIGOV_DIMDATASETEXPRESSIONS_SCAN_ADD | TASK_PBIGOV_DIMDATASETEXPRESSIONS_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATASETEXPRESSIONS | PBIGOV.V_DIMDATASETEXPRESSIONS
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 100 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasetroles_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETROLES_SCAN | PBIGOV_DATASETROLES_SCAN | STM_PBIGOV_DATASETROLES_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETROLES_SCAN | USING CRON 0 4 * * * UTC | PBIGOV_DATASETROLES_SCAN | V_PBIGOV_DIMDATASETROLES_SCAN | PBIGOV_DIMDATASETROLES_SCAN_ADD | TASK_PBIGOV_DIMDATASETROLES_SCAN | USING CRON 0 5 * * * UTC | PBIGOV.DIMDATASETROLES | PBIGOV.V_DIMDATASETROLES
Medium | In progress | Not started | Samir | 2025-03-19 |  |  | 100 |  | ci-dev-df-pbiapi-awss3-scanner-* | la-pbigov-dev-scanner-* | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | datasettableexpressions_scan | Dimension table, Scanner data | PIPE_PBIGOV_DATASETTABLEEXPRESSIONS_SCAN | PBIGOV_DATASETTABLEEXPRESSIONS_SCAN | STM_PBIGOV_DATASETTABLEEXPRESSIONS_SCAN | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_DATASETTABLEEXPRESSIONS_SCAN | USING CRON 0 8 * * * UTC | PBIGOV_DATASETTABLEEXPRESSIONS_SCAN | V_PBIGOV_DIMDATASETTABLEEXPRESSIONS_SCAN | PBIGOV_DIMDATASETTABLEEXPRESSIONS_SCAN_ADD | TASK_PBIGOV_DIMDATASETTABLEEXPRESSIONS_SCAN | after DEV.CONFORMED.TASK_PBIGOV_START | PBIGOV.DIMDATASETTABLEEXPRESSIONS | PBIGOV.V_DIMDATASETTABLEEXPRESSIONS
Low | In progress | Not started | Samir | TBD |  |  | 100 | Data is not extracted yet | ci-dev-df-pbiapi-awss3-groups-full | la-pbigov-dev-groups | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | reportpages | Dimension table | PIPE_PBIGOV_REPORTPAGES | PBIGOV_REPORTPAGES | STM_PBIGOV_REPORTPAGES | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_REPORTPAGES | USING CRON 0 4 * * * UTC | PBIGOV_REPORTPAGES | V_PBIGOV_DIMREPORTPAGES | PBIGOV_DIMREPORTPAGES_ADD | TASK_PBIGOV_DIMREPORTPAGES | USING CRON 0 5 * * * UTC | PBIGOV.DIMREPORTPAGES | PBIGOV.V_DIMREPORTPAGES
Medium | Not started | Not started | Ruslan | TBD |  |  | 100 |  | ci-dev-df-pbipsh-awss3-gatewaylogs-incr | la-pbigov-dev-gatewaylogs | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | gatewaylogs | Fact table | PIPE_PBIGOV_GATEWAYLOGS | PBIGOV_GATEWAYLOGS | STM_PBIGOV_GATEWAYLOGS | TABLE_LOAD_DELTA_ADD | TASK_PBIGOV_GATEWAYLOGS | USING CRON 0 4 * * * UTC | PBIGOV_GATEWAYLOGS | V_PBIGOV_FACTGATEWAYLOGS | PBIGOV_FACTGATEWAYLOGS_ADD | TASK_PBIGOV_FACTGATEWAYLOGS | USING CRON 0 5 * * * UTC | PBIGOV.FACTGATEWAYLOGS | PBIGOV.V_FACTGATEWAYLOGS
High | Completed | Not started | Samir | 2025-06-18 | Samir |  | 100 |  |  |  | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | dataflowrefreshhistory | Fact table | PIPE_PBIGOV_DATAFLOWREFRESHHISTORY | PBIGOV_DATAFLOWREFRESHHISTORY | STM_PBIGOV_DATAFLOWREFRESHHISTORY | TABLE_LOAD_DELTA_ADD | TASK_PBIGOV_DATAFLOWREFRESHHISTORY | USING CRON 0 4 * * * UTC | PBIGOV_DATAFLOWREFRESHHISTORY | V_PBIGOV_FACTDATAFLOWREFRESHHISTORY | PBIGOV_FACTDATAFLOWREFRESHHISTORY_ADD | TASK_PBIGOV_FACTDATAFLOWREFRESHHISTORY | USING CRON 0 5 * * * UTC | PBIGOV.FACTDATAFLOWREFRESHHISTORY | PBIGOV.V_FACTDATAFLOWREFRESHHISTORY
Medium | Not started | Not started | TBD | TBD |  |  | 100 |  | ci-dev-df-pbiapi-awss3-gitconnections-full | la-pbigov-dev-gitconnections | Daily, 01:00 AM | Daily, 02:00 AM | s3-eip-dev-uea1-landing-001 | landing/data/pbi | gitconnections | Dimension table | PIPE_PBIGOV_GITCONNECTIONS | PBIGOV_GITCONNECTIONS | STM_PBIGOV_GITCONNECTIONS | TABLE_LOAD_FULL_ADD | TASK_PBIGOV_GITCONNECTIONS | USING CRON 0 4 * * * UTC | PBIGOV_GITCONNECTIONS | V_PBIGOV_DIMGITCONNECTIONS | PBIGOV_DIMGITCONNECTIONS_ADD | TASK_PBIGOV_DIMGITCONNECTIONS | USING CRON 0 5 * * * UTC | PBIGOV.DIMGITCONNECTIONS | PBIGOV.V_DIMGITCONNECTIONS

## Sheet2
dataflowrefreshschedules_scan | dataflowId (id) AS ArtifactId
UNION
datasetdqrefreshschedules_scan | datasetid (id)
datasetrefreshschedules_scan | datasetid (id)
refreshschedules | datasetid (refreshableid)
artifactid

## Tables Load Order
Batch # | Table Name | Dependency
1 | DIMDOMAINS | -
| DIMCAPACITIES | -
| DIMGATEWAYCLUSTERS | -
| DIMDEPLOYMENTPIPELINES | -
2 | DIMGATEWAYCLUSTERPERMISSIONS | DIMGATEWAYCLUSTERS
| DIMGATEWAYINSTANCES | DIMGATEWAYCLUSTERS
| DIMARTIFACTDATASOURCEDETAILS | DIMGATEWAYCLUSTERS
| DIMWORKSPACES | DIMDOMAINS, DIMCAPACITIES
3 | DIMAPPS | DIMWORKSPACES
| DIMDATASETS | DIMWORKSPACES
| DIMDATAFLOWS | DIMWORKSPACES
| DIMDATAMARTS | DIMWORKSPACES
| DIMEXPLORATIONS | DIMWORKSPACES
| DIMFABRICARTIFACTS | DIMWORKSPACES
| DIMWORKBOOKS | DIMWORKSPACES
| DIMDEPLOYMENTPIPELINESTAGES | DIMWORKSPACES
4 | DIMREPORTS | DIMWORKSPACES, DIMAPPS, DIMDATASETS
| DIMREFRESHSCHEDULES | DIMDATASETS
| DIMDATASETTABLES | DIMDATASETS
| DIMDATASETCOLUMNS | DIMDATASETS
| DIMDATASETMEASURES | DIMDATASETS
| FACTLASTREFRESHES | DIMDATASETS
| DIMDATAFLOWPARTITIONS | DIMDATAFLOWS
| DIMDATAFLOWQUERIES | DIMDATAFLOWS
5 | DIMUPSTREAMARTIFACTS | DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS
| DIMDASHBOARDS | DIMWORKSPACES, DIMAPPS, DIMREPORTS, DIMDATASETS
| DIMARTIFACTDATASOURCES | DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS, DIMFABRICARTIFACTS, DIMWORKBOOKS
6 | DIMDASHBOARDTILES | DIMDASHBOARDS
| DIMARTIFACTUSERS | DIMCAPACITIES, DIMDEPLOYMENTPIPELINES, DIMWORKSPACES, DIMAPPS, DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS, DIMEXPLORATIONS, DIMFABRICARTIFACTS, DIMWORKBOOKS, DIMREPORTS, DIMDASHBOARDS
| DIMARTIFACTRELATIONS | DIMCAPACITIES, DIMDEPLOYMENTPIPELINES, DIMWORKSPACES, DIMAPPS, DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS, DIMEXPLORATIONS, DIMFABRICARTIFACTS, DIMWORKBOOKS, DIMREPORTS, DIMDASHBOARDS
7 | FACTACTIVITYLOGS | DIMCAPACITIES, DIMDEPLOYMENTPIPELINES, DIMWORKSPACES, DIMAPPS, DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS, DIMEXPLORATIONS, DIMFABRICARTIFACTS, DIMWORKBOOKS, DIMREPORTS, DIMDASHBOARDS, DIMGATEWAYCLUSTERS
| FACTARTIFACTMETRICS | DIMDATASETS, DIMDATAFLOWS, DIMDATAMARTS, DIMEXPLORATIONS, DIMFABRICARTIFACTS, DIMWORKBOOKS, DIMREPORTS, DIMDASHBOARDS

## Sheet1
Replaced Text | Replaced Text
V_PBIGOV_DIMWORKSPACES | activitylogs | activitylogs | TRUE
V_PBIGOV_DIMREPORTS | apps | apps | TRUE
V_PBIGOV_DIMDATASETS | appusers | appusers | TRUE
V_PBIGOV_DIMDATAFLOWS | artifactmetrics | artifactmetrics | TRUE
V_PBIGOV_DIMDASHBOARDS | capacities | capacities | TRUE
V_PBIGOV_DIMWORKBOOKS | capacityartifacts | capacityartifacts | TRUE
V_PBIGOV_DIMWORKSPACEUSERS | capacityusers | capacityusers | TRUE
V_PBIGOV_DIMDATASETTABLES | dashboards | dashboards | TRUE
V_PBIGOV_DIMDATASETCOLUMNS | dashboards_scan | dashboards_scan | TRUE
V_PBIGOV_DIMDATASETMEASURES | dashboardtiles_scan | dashboardtiles_scan | TRUE
V_PBIGOV_DIMDATASETUPSTREAMDATASETS | dashboardusers_scan | dashboardusers_scan | TRUE
V_PBIGOV_DIMDATASETUPSTREAMDATAFLOWS | dataflowdatasources_scan | dataflowdatasources_scan | TRUE
V_PBIGOV_DIMDATAFLOWUPSTREAMDATAFLOWS | dataflowrefreshschedules_scan | dataflowpartitions_json | FALSE
V_PBIGOV_DIMDATASOURCES | dataflows | dataflowqueries_json | FALSE
V_PBIGOV_DIMDATASETDATASOURCES | dataflows_scan | dataflowrefreshschedules_scan | FALSE
V_PBIGOV_DIMDATAFLOWDATASOURCES | dataflowupstreamdataflows_scan | dataflows | FALSE
V_PBIGOV_DIMAPPS | dataflowusers_scan | dataflows_json | FALSE
V_PBIGOV_DIMAPPUSERS | datamarts_scan | dataflows_scan | FALSE
V_PBIGOV_DIMCAPACITIES | datamartusers_scan | dataflowupstreamdataflows_scan | FALSE
V_PBIGOV_DIMCAPACITYUSERS | datapipelines_scan | dataflowusers_scan | FALSE
V_PBIGOV_DIMGATEWAYS | datapipelineusers_scan | datamartdatasources_scan | FALSE
V_PBIGOV_FACTGATEWAYLOGS | datasetcolumns_scan | datamarts_scan | FALSE
V_PBIGOV_DIMEMPLOYEES | datasetdatasources_scan | datapipelines_scan | FALSE
V_PBIGOV_DIMLICENSES | datasetmeasures_scan | datapipelineusers_scan | FALSE
V_PBIGOV_DIMREFRESHSCHEDULES | datasets | datasetcolumns_scan | FALSE
V_PBIGOV_FACTLASTREFRESHES | datasets_scan | datasetdatasources_scan | FALSE
V_PBIGOV_DIMPIPELINES | datasettables_scan | datasetmeasures_scan | FALSE
V_PBIGOV_DIMPIPELINESTAGES | datasetupstreamdataflows_scan | datasets | FALSE
V_PBIGOV_DIMPIPELINEUSERS | datasetupstreamdatasets_scan | datasets_scan | FALSE
V_PBIGOV_FACTARTIFACTMETRICS | datasources_scan | datasettables_scan | FALSE
V_PBIGOV_DIMCAPACITYARTIFACTS | domains | datasetupstreamdataflows_scan | FALSE
V_PBIGOV_FACTACTIVITYLOGS | environments_scan | datasetupstreamdatasets_scan | FALSE
V_PBIGOV_DIMSERVICEPRINCIPALPERMISSIONS | environmentusers_scan | datasetusers_scan | FALSE
V_PBIGOV_ACTIVEWORKSPACES | eventstreams_scan | datasources_scan | FALSE
| eventstreamusers_scan | domains | FALSE
| explorations_scan | eventhouses_scan | FALSE
| explorationusers_scan | eventhouseusers_scan | FALSE
| gatewayclusterpermissions | eventstreams_scan | FALSE
| gatewayclusters | eventstreamusers_scan | FALSE
| gatewayinstances | explorations_scan | FALSE
| gatewaylogs | explorationusers_scan | FALSE
| kqldatabases_scan | gatewayclusterpermissions | FALSE
| kqldatabaseusers_scan | gatewayclusters | FALSE
| lakehouses_scan | gatewayinstances | FALSE
| lakehouseusers_scan | kqldatabases_scan | FALSE
| lastrefreshes | kqldatabaseusers_scan | FALSE
| mlexperiments_scan | lakehouses_scan | FALSE
| mlexperimentusers_scan | lakehouseusers_scan | FALSE
| mlmodels_scan | lastrefreshes | FALSE
| mlmodelusers_scan | mlexperiments_scan | FALSE
| notebooks_scan | mlexperimentusers_scan | FALSE
| notebookusers_scan | mlmodels_scan | FALSE
| orgapps_scan | mlmodelusers_scan | FALSE
| orgappusers_scan | notebooks_scan | FALSE
| pipelines | notebookusers_scan | FALSE
| pipelinestages | orgapps_scan | FALSE
| pipelineusers | orgappusers_scan | FALSE
| reflexes_scan | pipelines | FALSE
| reflexusers_scan | pipelinestages | FALSE
| refreshschedules | pipelineusers | FALSE
| reportpages | reflexes_scan | FALSE
| reportrelations_scan | refreshschedules | FALSE
| reports | reportrelations_scan | FALSE
| reports_scan | reports | FALSE
| sqlanalyticsendpoints_scan | reports_scan | FALSE
| sqlanalyticsendpointusers_scan | sqlanalyticsendpoints_scan | FALSE
| sqldatabases_scan | sqlanalyticsendpointusers_scan | FALSE
| sqldatabaseusers_scan | warehouses_scan | FALSE
| warehouses_scan | warehouseusers_scan | FALSE
| warehouseusers_scan | workbooks | FALSE
| workbooks | workspaces | FALSE
| workspaces | workspaces_scan | FALSE
| workspaces_scan | workspaceusers | FALSE
| workspaceusers | workspaceusers_scan | FALSE
workspaceusers_scan

## Summary
Scripts |  |  | Snowflake coding |  |  | Power BI reports
Not started | In Progress | Completed | Not started | In Progress | Completed | Not started | In Progress | Completed
4 | 77 | 12 | 91 | 2 | 0